## Slide 1: Rapid Assurance Review: Guideline and Presentation
Digital Restart Fund (DRF) Rapid Assurance Review

## Slide 2: Digital Restart Fund (DRF) Rapid Assurance Review
To ensure NSW Government projects funded through the Digital Restart Fund achieve successful outcomes, on time and on budget, through a risk-based, fit for purpose assurance process.
To reduce delivery risk and improve delivery confidence for smaller DRF investments catering for agile delivery methods and digital transformation.
To help Sponsors and projects be successful.
Objectives

## Slide 3: DRF Rapid Assurance Reviews and Confidentiality
      Reviews are structured, expert peer reviews performed at critical points during the project lifecycle
      Are not an audit
      Provide a point in time snapshot of project performance, risks and issues
      Help inform NSW Cabinet on delivery progress
      Help Projects and Sponsors achieve their intended outcomes, on budget, on time
      Are independent and confidential - interview discussions are not / should not be repeated
      Encourage open and frank conversations - findings / discussions are not attributed to individuals, interviews with individuals (not groups)

## Slide 4: DRF Rapid Assurance Reviews
 |  | YOU ARE HERE | Supplementary reviews for digital projects following the stages of service design and delivery |  |  | 
 | Mobilisation | Delivery | End of Alpha | In Private Beta | In Public Beta | Ready to Release
Purpose | The project is set-up to succeed considering delivery approach and plans, clarity on business problem and target state, governance, project management and resourcing arrangements | To provide confidence that delivery is well managed. | The project is delivering to user needs, continues to be achievable, processes support stakeholder review and feedback, users are being prepared for transition | Outcomes support a clear user demand, user needs are being met, business target state and benefits are achievable, plans for scaling are feasible | Delivery is on track to meet user needs and target state, project continues to be achievable, will provide sufficient business value. Plans for production release and transition are viable and adequate | To provide confidence that the business is prepared to accept the change (people, process, systems)
Areas of Focus | Selection of Delivery Approach Clear Vision, Business Problem, User Needs Benefit Realisation and Risk Management Resource Capability and Planning Governance Current Phase Design Standard Considerations at Discovery Phase (Digital projects only) | Benefits Management Scope Management Schedule Management Budget and Cost Management Quality and Agile Effectiveness Risk Management Governance Stakeholder Management | Delivery Focus Areas Plus Stakeholder Management & Feedback Progress Tracking and Reporting Change Management Technical Debt and Defect Resolution Resource Capability, Capacity and Planning Compliance with NSW Design Standards | Delivery Focus Areas Plus Private Beta results Transition Planning and Change Management Progress Tracking and Reporting Budget Tracking Design Standard Considerations at Beta Phase | Delivery Focus Areas Plus Public Beta results Transition Planning and Change Management Progress Tracking and Reporting Budget Tracking Design Standard Considerations at Beta Phase | Production Release Progress and Target State Value/ Benefit Realisation Risk Management Change Management Readiness for Operating Phase and transition to Business as Usual Design Standard considerations (for Digital projects only)

## Slide 5: Delivery Review
Purpose
    Determine if project delivery is well managed
Assess whether the project is delivering to user needs, continues to be achievable, and processes support stakeholder review and feedback.
Assess whether outcomes support a clear user demand, user needs are being met, business target state and benefits are achievable, plans to scale are feasible.
Determine if delivery is on track to meet target state, project remains achievable and will provide sufficient business value. Plans for production and transition are viable and adequate.
End of Alpha:
In Private Beta:
In Public Beta:
For Digital Projects following the Stages of Service Design and Delivery

## Slide 6: DRF Rapid Assurance | Review Steps
Interviews & Ceremony observations
Report writing
Project Risk Assessment completed with Project Owner / Project Manager
IDIA meets with Sponsor to discuss upcoming Review
Project Coordinator to upload Project documents
Sponsor completes End-of-Review Survey
PLANNING MEETING (Sponsor, PM, IDIA & Review Team)
IDIA nominates Review Team & works with Project Coordinator to plan for review
IDIA develops Assurance Plan
Review Team reviews response &
IDIA issues Final Report
SPONSOR DEBRIEF
Draft Report issued
Agency Response: Fact Check, Action Plans, Sponsor Comment
2 days prior Planning Meeting
Held during week prior to Interviews
2 days
1 day
2 days

## Slide 7: Overview of Agency Support Requested
 | Project documentation – upload to SharePoint
 | Planning day meeting room and conference call set up
 | Planning meeting invitation
 | Planning meeting project presentation
 | Interview schedule/register (prefer 1 person per interview)
 | Document register – SharePoint
 | Interview room: Internet access Report writing room with screen
 | Ceremony and Interview invitations including MS Teams link
 | Sponsor Debrief invitation including MS Teams link
 | Additional documentation and interview requests from the review team
 | Building access for review team if onsite

## Slide 8: Delivery Review Areas of Focus
The project is delivering iteratively, enabling early realisation of benefits
Evidence that the Backlog is updated and prioritised by key stakeholders regularly
Development of a Release Plan that shows how the capabilities or features in the Product Roadmap will be delivered
The use of agile metrics to understand capacity, constraints and progress
Alignment between the budget planned for the Product Roadmap and the forecast costs of the Release Plan
All deliverables have an effective Definition of Done that is well understood and sets minimum quality requirements
Agile ways of working and ceremonies are effective
Risks are being managed through delivery of MVP, use of proof of concepts, prototypes
Processes are in place to seek feedback early and often
Governance is operating effectively and close engagement exists between the Sponsor, Product Owner and delivery team(s)
Key stakeholders are fully engaged in the definition of scope, prioritisation of features and review of outputs

## Slide 9: Delivery Review
Additional Areas of focus at end of Alpha Stage
      The project is delivering to its objectives and user needs
      Budget and spend is on track
      Governance arrangements are appropriate for managing when tolerances are exceeded
      Agile processes support stakeholder review and feedback and changing business priorities
      Users are being adequately prepared for the transition to new / redesigned digital services
      Time has been planned to prioritise and fix technical debt and defects
      Resource capability and capacity requirements are assessed and secured for the next phase
      Consideration and application of the NSW Design Standards
Notes: Delete slide if not relevant

## Slide 10: Delivery Review
Additional Areas of focus in Private Beta Stage
      Business testing arrangements are sufficient
      Outcomes of private beta testing support a clear user demand for the service, user needs are being met, and business target state and benefits are achievable
      Plans for scaling the service / solution for public beta or production release are feasible and viable for a larger number of users
      Change management activities and transition plans are adequate
      Risk management processes are effective
      Progress is being tracked and reported
      Budget and spend is on track
      Consideration and application of the NSW Design Standards
Additional Areas of focus in Public Beta Stage
      Business testing arrangements are sufficient
      Outcomes of public beta testing support a clear user demand for the service, user needs are being met, and business target state and benefits are achievable
      Plans for scaling the service / solution for production release are feasible and viable
      Change management activities and transition plans are adequate
      Risk management processes are effective
      Progress is being tracked and reported
      Budget and spend is on track
      Consideration and application of the NSW Design Standards
Notes: Delete slide if not relevant

## Slide 11: Delivery Review
Outputs include:
  End of Day updates to Sponsor during the interview period
  Sponsor Debrief (coinciding with issue of Draft Report)
  The Final Report covering:
      Review Team’s delivery confidence assessment rating i.e. High / Medium to High / Medium / Medium to Low / Low
      Detailed Recommendations and ratings i.e. Critical / Essential / Recommended
      Sponsor’s acknowledgement & comments
      Agency’s Recommendation responses / agency action plan
      Agreement on next Review timing (if applicable)

## Slide 12: Supporting Documentations
DRF funding letter
Lean Business Case
Inputs for Statutory Treasury Reporting (ISTR)
Delivery and Performance Architecture (DAPA)
Summary of any changes and impacts to the business case
Agile artefacts (e.g. meeting cadence, Product Backlog, DoDs, Release Plan, Iteration Plan, Sprint Strategy / Plan,
Outputs from Retrospective meetings and Showcases (last 3 months)
Definition / analysis of business problem
Business target state / success criteria
Product Roadmap
Delivery approach
Governance structure
Project Board Reports and Minutes (last 3 meetings)
Project Status reports / agile metrics e.g. sprint burn-down (last 3 months)
Project schedule
Resource plan, RACI
Financials – Spend to Date, Current ETC and Approved Budget
Benefits Plan, Map or Register
Project Risk and Issue Register
Cyber Risk Assessment
Quality Plan including Go No-Go criteria
Supplier plans for development and implementation (as relevant)
Security Review plans and results
Test Plans and Test Reports
User Feedback
Change Management Plan
Training plan
Contingency / Business Continuity plans
Deployment and Implementation Plan
Service Management arrangements